## Plan
Week | Date | Member1 (Lead/Arch) | Member2 (Video Prep) | Member3 (Data Label) | Member4 (Model Train) | Member5 (Backend/Rules/Agent) | Member6 (Frontend/Test) | Weekly Deliverables
Week 1 | 2026/03/30-2026/04/05 | Finalize scope; confirm YOLO version and Agent principles; set milestones | Build FFmpeg frame extraction scripts; unify resolution/FPS standards | Define labeling standards (classes, naming, QA rules); sort data sources | Set up training environment; run YOLO baseline training pipeline | Build FastAPI skeleton; complete /health and base routes | Build homepage shell; complete video view and bbox placeholder | Tech selection V1 + labeling standard V1 + runnable baseline demo
Week 2 | 2026/04/06-2026/04/12 | Weekly review; track schedule deviations; coordinate API integration | Finish first-batch video preprocessing and frame extraction | Finish first-batch labels (target 3000+); complete 10% QA review | Train YOLO v1; output first-round metrics and error cases | Implement core boundary/dwell logic; detect only in warning regions | Implement bbox + confidence display; connect Agent entry on homepage | dataset_v1 + weights_v1 + initial rules engine + initial frontend visualization
Week 3 | 2026/04/13-2026/04/19 | Push module integration; run performance??; freeze beta scope | Enhance low-light/backlight samples; add hard examples | Incremental labeling (target 2000+); output hard-case set | Train YOLO v2/v3 and tune; compare split-training vs merged-training | Deliver minimal /agent/chat; complete .env loading and status API | Complete E2E integration; run stability and response-time tests | Beta package (detection+rules+Agent+replay) + integration issue list
Week 4 | 2026/04/20-2026/04/26 | Organize acceptance; output final review; release delivery version | Archive data/scripts; complete preprocessing docs | Output final dataset version and QA report | Output final model (best.pt) and performance report | Finalize one-click scripts and API docs | Complete regression tests, demo rehearsal, deployment acceptance | Release v1.0 package + test report + deployment guide + defense materials

## Roles
Member | Role | Main Responsibility | Weekly Output
Member1 | Lead/Architecture | Requirement breakdown, schedule management, release control, risk management | Weekly plan updates, risk list, milestone acceptance notes
Member2 | Video Preprocessing | FFmpeg frame extraction, low-light preprocessing, data cleaning | Preprocessing scripts, sample pack, abnormal sample logs
Member3 | Data Labeling | Data collection, labeling, QA review, dataset versioning | Label progress sheet, QA report, dataset release notes
Member4 | Model Training | YOLO training, hyper-parameter tuning, model evaluation, export | Training logs, metrics report, best/last weights
Member5 | Backend/Rules/Agent | Rules engine, API development, Agent tool orchestration | API change log, self-test output, interface docs
Member6 | Frontend/Integration/Test | Frontend display, bbox visualization, integration testing, deployment validation | Integration records, test report, demo script